## Gantt Chart
STUDIO PROJECT SCHEDULE
PROJECT TITLE |  | Studio Project |  |  |  |  | COMPANY NAME | [6 empty] | Team 18
PROJECT MANAGER |  | Zhong Da, Alif, Kenneth, Ko Sand |  |  |  |  | DATE | [6 empty] | 2018-08-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Week 1
1.1 | Discuss Proposal |  | 2018-08-13 | 2018-08-13 | 1 | 0% | bar: WEEK 1 M; WEEK 2 W
1.2 | Map & Level Design |  | 2018-08-14 | 2018-08-16 | 3 | 0% | bar: WEEK 1 T to WEEK 1 R; WEEK 2 W
1.3 | Player Design |  | 2018-08-14 | 2018-08-16 | 3 | 0% | bar: WEEK 1 T to WEEK 1 R; WEEK 2 W
1.4 | Items & Puzzles Design |  | 2018-08-14 | 2018-08-16 | 3 | 0% | bar: WEEK 1 T to WEEK 1 R; WEEK 2 W
1.5 | Movement Mechanics |  | 2018-08-14 | 2018-08-16 | 3 | 0% | bar: WEEK 1 T to WEEK 1 R; WEEK 2 W
1.6 | Progress Check |  | 2018-08-17 | 2018-08-17 | 1 | 0% | bar: WEEK 1 F; WEEK 2 W
2 | Week 2
2.1 | Level Dialog Boxes |  | 2018-08-20 | 2018-08-22 | 3 | 0% | bar: WEEK 2 M to WEEK 2 W
2.2 | Player Interaction & Collision |  | 2018-08-20 | 2018-08-22 | 3 | 0% | bar: WEEK 2 M to WEEK 2 W
2.3 | Item Crafting |  | 2018-08-20 | 2018-08-22 | 3 | 0% | bar: WEEK 2 M to WEEK 2 W
2.4 | Progress Check |  | 2018-08-22 | 2018-08-22 | 1 | 0% | bar: WEEK 2 W
2.5 | Implement new Features |  | 2018-08-22 | 2018-08-23 | 2 | 0% | bar: WEEK 2 W to WEEK 2 R
2.6 | Improve and Polish work |  | 2018-08-24 | 2018-08-24 | 1 | 0% | bar: WEEK 2 W; WEEK 2 F
2.7 | Mid-presentation |  | 2018-08-24 | 2018-08-24 | 1 | 0% | bar: WEEK 2 W; WEEK 2 F
3 | Week 3
3.1 | Debugging and Bug Fixes |  | 2018-08-27 | 2018-08-28 | 2 | 0% | bar: WEEK 2 W; WEEK 3 M to WEEK 3 T
3.2 | Optimize and Comment codes |  | 2018-08-27 | 2018-08-28 | 2 | 0% | bar: WEEK 2 W; WEEK 3 M to WEEK 3 T
3.3 | Progress Check |  | 2018-08-29 | 2018-08-29 | 1 | 0% | bar: WEEK 2 W; WEEK 3 W
3.4 | Final touch-up |  | 2018-08-29 | 2018-08-29 | 1 | 0% | bar: WEEK 2 W; WEEK 3 W
3.5 | Gameplay Demo |  | 2018-08-29 | 2018-08-29 | 1 | 0% | bar: WEEK 2 W; WEEK 3 W
3.6 | Compile Documents |  | 2018-08-29 | 2018-08-29 | 1 | 0% | bar: WEEK 2 W; WEEK 3 W
3.7 | Final Presentation + Report and submission |  | 2018-08-30 | 2018-08-30 | 1 | 0% | bar: WEEK 2 W; WEEK 3 R
4 | Final Presentation